## Sheet1
Name:
Date | Time-In | Time-Out | Total Hours | Reasons for absences | What did you accomplish today? | Did you face any issue
4/20/2020
4/21/2020 | 19.00 PM | 23.00 PM | 4 hours |  | I opened the mail in which the project information was described. Then I tried to scrape Linkedin and naukri.com first as it is better in updating information comparing to others. But unfortunately I was blocked because of its firewall which treated my request as a attack. So I tried to use proxy IP address. But that dint work for me well. So I skipped to the next website i.e. Shine.com . | I experienced trouble in accessing data of Linkedin and naukri.com and was unable to fetch request data succesully.
4/22/2020 | 15.00 PM | 17.30 PM | 2 hours 30 minutes |  | Today I tried another website which was mentioned in the mail, Shine.com to request Data and to prevent from blocking I first tried requesting a single data object and I was succesfull in getting Data back for the request.Even though it was raw data It can be modified or operated to get the required peices of information from it. In this module I used Beautifull soup Library to create a soup object and then get data. I also used urlib2 library to send request. | I dint face any problems today as shine.com firewall did not block my IP address and the data object was fetched.
4/23/2020 | 15.00 PM | 16.30 PM | 1 hour 30 minutes |  | I succesfully scraped the data from shine.com and saved in the csv in required format | no issues
4/24/2020 | 17.00 PM | 18.30 PM | 1 hour 30 minutes |  | I tried to use proxy servers and scrape data from Linked in and naukri.com | I was not able to scrape because the website firewall was blocking my every request
4/25/2020 | 17.00 PM | 18.30 PM | 1 hour 30 minutes |  | I had a discussion with Razyak sir and he assignd me a new task. I was working on it. | no issues
4/26/2020 | 12.30 PM | 13.30 PM | 1 hour | I have a online olympaid exam today ,so dedicated only 30 minutes. | I tried to scrape naukri.com. But it still dint work. | Unable to scrape naukri.com
4/27/2020 | 12.00 PM | 2.00 PM | 2 hours |  | I succesfully scraped data from shine.com and saved it in excel sheet | no issues
4/28/2020 | 6.00 PM | 9.00 PM | 3 hours |  | as mentioned in the new task I changed the parameters and code,after that I saved all the changes and data in a excel sheet.
4/29/2020 | 6.30 PM | 9.00 PM | 2hours 30 minutes |  | Succesfully exported data as metnioned in the task no 2 and shared the csv file on drive folder. | no issues
4/30/2020 | 6.00 PM | 7.00 PM | 1 hour |  | Completed the task and submitted the excel file in the drive folder | no issues.
2020-01-05 | 6.30 PM | 7.00 pm | 30 minutes |  | Submitted the first task and informed to rzyak sir about it, dint receive next task
2020-02-05 | 3.00 PM | 5.00 PM | 2 hours |  | received the next task from Rzyak sir
2020-03-05 | 6.00 PM |  |  |  | Working on the task 2 in which the user may enter the job role and place and the related jobs to excel sheet.
2020-04-05
2020-05-05
2020-06-05
2020-07-05
2020-08-05
2020-09-05
2020-10-05
2020-11-05
2020-12-05
5/13/2020
5/14/2020
5/15/2020
5/16/2020
2020-05-18
2020-05-19
2020-05-20